## Guidance
Test script
This test scipt is provided for your guidance during the User Acceptance Testing (UAT) phase of your Edays system implementation project. The test script is split into two areas- the admin panel and the front-end.
We recommend that you use this script in conjunction with your system setup questionnaire (SSQ) and data capture form (DCF) documents when checking the system meets your requirements.
Your project manager will have shared a defect log with you. If you encounter any issues or have any queries that cannot be answered by any of the articles in our knowledge base (https://support.e-days.com/support/home), please log them on the defect log, so your project manager can review this with you.
Top tips
To get the most out of the testing phase, we recommend you do the following:
1) If you have spare user accounts in the system, create a test user and a test authoriser and use these accounts to submit different types of requests in the system.
2) Ask a few standard users and their authorisers within your organisation to test the system themselves and provide you with their feedback.

## Admin panel
EDAYS TEST SCRIPT
Admin home | How/where | Expected behaviour | Useful links | User Testing This Feature | Additional Users Involved | Status | Observed Behaviour (If Unexpected) | Additional Comments (If Required)
Check that the list of administrators is correct | Go to "Admin Panel" under the "Admin Tools" section at the top of the screen, and review the list of names in the administrators droplet | Correct users will display in this list |  | ALL countries
Check you have a sufficient number of user licenses for your organisation | Go to "Admin Panel" under the "Admin Tools" section at the top of the screen, and check the details in the user breakdown droplet. | The number of licences should match the number that you ordered and the number in the available column should not be a negative number. | https://support.e-days.com/support/solutions/articles/77000230104-adding-user-licenses | ALL countries
Global settings | How/where | Expected behaviour | Useful links | User Testing This Feature | Additional Users Involved
Check the default system settings are correct | Go to "System Setup" under the "Global" section in the admin panel and check the settings applied. Please note: some of these settings may be overriden on the template level (if you have multiple countries in your system setup for example) or on a user level. | The default settings should match your requirements that are not specific to just a sub-set of your users or individuals. | https://support.e-days.com/support/solutions/articles/77000475993-user-view-configuration | ALL countries
Check the public holidays in your system are correct | Go to "Public Holiday Setup" under the "Global" section in the admin panel and check the dates are correct for each group by clicking the 'Days' button. | The correct public holiday dates are all provided for the current and next year. | https://support.e-days.com/support/solutions/articles/77000230832-public-holiday-import-via-import-feed https://support.e-days.com/support/solutions/articles/77000230166-updating-a-public-holiday-list https://support.e-days.com/support/solutions/articles/77000230164-adding-a-new-public-holiday-date | ALL countries
Check any custom days in your system are correct | Go to "Custom Days Setup" under the "Global" section in the admin panel and check the dates are correct for each group by clicking the 'Days' button. | The correct custom holiday dates are all provided for the current year, as per your system setup questionnaire. | https://support.e-days.com/support/solutions/articles/77000229990-custom-days-setup-adding-a-new-custom-days-date https://support.e-days.com/support/solutions/articles/77000230013-custom-days-setup-adding-a-new-custom-days-list | ALL countries
Rotas | Go to "Rota Setup" under the "Global" section in the admin panel and check the rota patterns in your system by clicking the 'Edit' button | The different rota patterns in this area reflect the working patterns for staff at your organisation, and, for any hours-based users, the duration is correct for each working day. | https://support.e-days.com/support/solutions/articles/77000230295-adding-a-new-days-rota https://support.e-days.com/support/solutions/articles/77000230294-adding-a-new-hours-rota https://support.e-days.com/support/solutions/articles/77000230293-adding-a-new-nights-rota
Groups | Go to "Group Setup" under the "Global" section in the admin panel and check the groups in each category by clicking the 'List' button. | All of the groups you require are listed under each category. If your requirements included minimum staffing levels, these will be reflected in the list for the relevant category in the minimum staff absent column. | https://support.e-days.com/support/solutions/articles/77000230093-editing-a-group https://support.e-days.com/support/solutions/articles/77000230097-adding-a-new-group https://support.e-days.com/support/solutions/articles/77000230090-adding-a-new-group-type https://support.e-days.com/support/solutions/articles/77000230095-deleting-a-group https://support.e-days.com/support/solutions/articles/77000230092-setting-a-minimum-staffing-level-for-a-group
Absence types | Go to "Absence Type Setup" under the "Global" section in the admin panel and check the settings for each of the absence types by clicking the 'Edit' button. | All of your specified absence types from the data capture form are listed in this section with the permissions set as required. Please note: some of the settings may be overridden for certain absence types on the template level (if different absence types are applicable for different countries for example) or on the user level (some administrators for example). | https://support.e-days.com/support/solutions/articles/77000487145-updating-absence-type-permissions-global-level https://support.e-days.com/support/solutions/articles/77000229974-adding-a-new-absence-type https://support.e-days.com/support/solutions/articles/77000229965-deleting-an-absence-type | ALL countries
Template settings | How/where | Expected behaviour | Useful links | User Testing This Feature | Additional Users Involved
Template settings | Go to "User templates" under the "Templates" section in the admin panel and click "edit" for the template you want to review the settings for. | The settings for the template are as specified on your system setup questionnaire. | https://support.e-days.com/support/solutions/articles/77000230302-changing-a-template-calendar-year https://support.e-days.com/support/solutions/articles/77000230560-changing-a-template-reporting-view https://support.e-days.com/support/solutions/articles/77000230561-changing-a-template-calendar-view https://support.e-days.com/support/solutions/articles/77000230566-changing-a-template-staff-records-view | ALL countries
Public holidays and custom days | Go to "User templates" under the "Templates" section in the admin panel, click "edit" for the template you want to review the public holidays and custom days for, select the rotas tab and click "apply public holidays" and "apply custom days" buttons to check the correct defaults are applied for the template. | The correct public holidays and custom days lists are applied to the template. You will be able to check the days in this list by reviewing the calendar grid underneath. | https://support.e-days.com/support/solutions/articles/77000230297-assigning-public-holidays-to-a-template-rota https://support.e-days.com/support/solutions/articles/77000230296-assigning-custom-days-to-a-template-rota
Absence types | Go to "User templates" under the "Templates" section in the admin panel, click "edit" for the template you want to review the absence type settings for, select the absence types tab and click "edit" to view the template specific settings for each absence type. Please note that the absence types may also be inheriting some additional settings from the "Global"-> "Absence type setup" area. | The absence types are configured based on the settings you specified on the data capture form. There are also some additional settings you may want to customise in this area ahead of releasing the system to your staff. | https://support.e-days.com/support/solutions/articles/77000230570-updating-an-absence-type-on-a-template
Overtime & TOIL types | Go to "User templates" under the "Templates" section in the admin panel, click "edit" for the template you want to review the overtime and TOIL type settings for and select the overtime & TOIL types tab. You will then see a summary of the booking settings for the overtime & TOIL types for this template and you can click the "Edit" button to either change these settings or view additional settings. | The overtime and TOIL types are enabled for each template based on the information supplied in your system setup questionnaire.
Entitlement request types | Go to "User templates" under the "Templates" section in the admin panel, click "edit" for the template you want to review the entitlement request type settings for, select the "entitlement request types" tab and click "edit" to view the template specific settings for each entitlement request type. Please note that if you have specified in your system setup questionnaire that you do not allow any employees to buy or sell their annual leave entitlements, this tab will not be present on the template. | All of the entitlement request types (e.g. selling annual leave days) are set to either allow or disallow bookings of that type depending on the details you specified in your system setup questionnaire. If there aren't any employees at your organisation for which entitlement request types are applicable, this tab will not be visible when reviewing the template settings. | https://support.e-days.com/support/solutions/articles/77000491468-enabling-or-disabling-flex-buy-selling-on-a-template-level
Entitlements | Go to "User templates" under the "Templates" section in the admin panel, click "edit" for the template you want to review the entitlement settings for and select the entitlements tab. You will then see a summary of the planned entitlement pots enabled on the template. You can click the orange "advanced" button to see the unplanned entitlement pots that have been enabled for the template also. Then you can click on the "edit" button for the entitlement pot you want to review, and either click "edit" to review the default settings for the entitlement element, or "policies" to review any accruals for the entitlement element, such as long service awards. | All of the entitlement pots that are relevant for the template are enabled, the carryover settings as specified on your system setup questionnaire are applied for the entitlement element when you click "edit" to view the element settings, and the accrual policies for the element match your requirements. | https://support.e-days.com/support/solutions/articles/77000450495-enabling-an-entitlement-on-a-template-level https://support.e-days.com/support/solutions/articles/77000450494-disabling-an-entitlement-on-a-template-level https://support.e-days.com/support/solutions/articles/77000481350-configuring-carryover-template-advanced-entitlement-mode | ALL countries
Users | How/where | Expected behaviour | Useful links | User Testing This Feature | Additional Users Involved
Entitlements | Go to "Users" under the "Users" section in the admin panel, click "edit" for the user you want to review the entitlements for and select the entitlements tab. You will then see a summary of the planned entitlement pots enabled on the template. You can click the orange "advanced" button to see the unplanned entitlement pots that have been enabled for the template also. Then you can click on the "edit" button for the entitlement pot you want to review, and either click "edit" to review the entitlement for that employee, or "policies" to review any accruals that are enabled for them. If you do click "edit" for the entitlement element, you will also be able to adjust the entitlement balance for the employee if required. Please note: if you want to review entitlements for all employees, we recommend that you run the "entitlement this year" report in the front-end of the system. | Users have the correct entitlement balances. | https://support.e-days.com/support/solutions/articles/77000230858-advanced-entitlement-set-up-updating-a-users-holiday-entitlement https://support.e-days.com/support/solutions/articles/77000230863-bulk-updating-users-entitlement https://support.e-days.com/support/solutions/articles/77000434384-running-an-entitlement-this-year-report
Rotas | Go to "Users" under the "Users" section in the admin panel, click "edit" for the user you want to review the rota for and select the rota tab. You can then select "apply rota", "apply public holidays" and "apply custom days" to review which rota the user is assigned to, as well as the public and custom days lists that have been applied for them. |  | https://support.e-days.com/support/solutions/articles/77000230885-changing-a-users-rota
User views | Go to "Users" under the "Users" section in the admin panel, click "edit" for the user you want to check the user views for and select the "system" tab. You can then scroll down to the user view settings area where you will be able to see the settings applied for them. | The user view settings match the ones in the system setup questionnaire, with administrators given access to view everyone. | https://support.e-days.com/support/solutions/articles/77000475993-user-view-configuration
Roles | Go to "Users" under the "Users" section in the admin panel, click "edit" for the user you want to check the role for and select the "roles" tab. | Users are correctly assigned the standard user, standard authoriser or standard administrator role. | https://support.e-days.com/support/solutions/articles/77000230263-roles-assign-or-alter-the-roles-applied-to-a-user
Records | How/where | Expected behaviour |  | User Testing This Feature | Additional Users Involved
Absence records | Go to "Absence records" under the "Records" section in the admin panel and review the absence records in the list. You can filter the records by user, absence type or date etc.by using the options at the top of this page. | The records displayed in this area are all correct, as per your data capture form. If you need to add any additional absence records, you can click the "add new" button, fill in the details in the fields provided and then either press "save" or "save and add another". | https://support.e-days.com/support/solutions/articles/77000230216-absences-adding-an-absence-record-via-admin-panel https://support.e-days.com/support/solutions/articles/77000230213-updating-an-absence-record | ALL countries
Carryover records | Go to "carryover / transfer records" under the "Records" section in the admin panel and review the carryover records in the list. You can filter the records by use or transfer type etc.by using the options at the top of this page. | The records displayed in this area are all correct, as per your data capture form. | https://support.e-days.com/support/solutions/articles/77000230191-carryover-transfers-adding-a-transfer-carryover-record-via-admin-panel https://support.e-days.com/support/solutions/articles/77000230189-updating-a-transfer-carryover-record | ALL countries
Additional modules | How/where | Expected behaviour | Useful links | User Testing This Feature | Additional Users Involved
Document portal | Go to "roles" under the "Global" section in the admin panel and check that standard administrators have the "document portal admin" box ticked in the "Administrator Access Permissions" section and that all roles have the "Document Portal" permission ticked in the "HR Access Permissions". You can then begin adding documents to the document portal by going to the "document portal" area in the "global" dropdown and selecting "add categories". Once you have uploaded your documents in your newly created document portal categories, you should be able to view these in the front-end by selecting the "document portal" under "my tools". | Admins have access to edit the document portal, and all user groups can view this section in the front-end and the documents you have uploaded. | https://support.e-days.com/support/solutions/articles/77000486027-configuring-the-document-portal https://support.e-days.com/support/solutions/articles/77000504611-roles-hr-role-permissions | ALL countries
Employee directory | Go to "roles" under the "Global" section in the admin panel and check that standard administrators have the "profile editor" box ticked in the "HR Access Permissions" section and that all user groups have the "profile viewer" permission ticked. Then, go to "system setup" in the "global" dropdown, and check you are happy with the default user view permissions for this area. You will then need to add the categories you require for the employee directory by selecting "user document categories" in the "users" dropdown and click the "add new document category" button. Once you have created the categories, you will need to upload the documents for each employee in the front-end by selecting the "employee directory" under the "my tools" dropdown. | Admins can edit the employee directory, all roles can access the employee directory and the visibility permissions are set to your requirements. You can also upload the appropriate documents for each employee in the front-end once you have created the document categories in the admin panel. | https://support.e-days.com/support/solutions/articles/77000488782-configuring-the-employee-directory https://support.e-days.com/support/solutions/articles/77000488784-using-the-employee-directory

## Front-end
EDAYS TEST SCRIPT
Manager Dashboard | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved | Status | Observed Behaviour (If Unexpected) | Additional Comments (If Required)
Check that you have visibility of the correct users in your calendar | Go to "Group Calendar" under the "My Tools" section at the top of the screen | Correct users will display dependant on your visibility settings | ALL countries
Filter the calendar by Groups | Use the "Group By" drop down at the top left of the calendar | You will be able to filter the users in the calendar by groups | ALL countries
Filter the calendar by a user or a group | Use the Search Bar at the top right of the calendar | You will be able to search for a specific user or a specific group | ALL countries
Select a user from the calendar and visit their staff record | Click on a User | If you are a manager you will be able to visit the staff record of your reportees, if you are an Administrator you will be able to visit the staff records of all users unless your requirements have specified changes to these default settings | ALL countries
Staff Records | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Check the data on the Personal dashboard of a user (e.g Personal/Entitlement information) | Select a User from the calendar or search them using the search bar at the top of the screen | The personal and entitlement information that has been provided for this user will populate here | ALL countries
Book a Holiday absence on behalf of a user | Click the "Holiday and Planned Records" button on the Users dashboard | The absence will be booked and a green banner will be displayed along the top of the screen to confirm this - the user should receive an email | ALL countries
Check that the correct duration has deducted from the Holiday entitlement | See the "Entitlement Information" section on the Users dashboard | The absence duration booked will deduct from the entitlement balance | ALL countries
Check that the absence requested has been added to the Absence Records list | Go to the "Absence Records" section under the "Admin" tab at the top of the screen | The absence record will be added to the list - if you are the users authoriser then the absence record will have a status of Authorised, if not, it will be Pending | ALL countries
Reports Dashboard | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Run a system report | Front End > "Manager Tools" > "Reports Dashboard" > "Data Reports" > "Run Report" | The chosen report will run and the results will be displayed within e-days | ALL countries
Create a custom report | Click "Create Report" and select the type of report. Then choose all the fields you wish to include | You will be able to create your own report selecting your chosen fields and filters | ALL countries
Run a custom report | Once done the above, click run at the top of the screen | Your report will run and the results will be displayed within e-days | ALL countries
Check that you have visibility of the correct users in the report | Reviewing the list of users displayed in the report you have run | Correct users will display dependant on your visibility settings | ALL countries
Download a report | Click "Download" at the top of the report you have run | You will be able to download your report in your chosen file format | ALL countries
Save a custom report | Click "Save" at the top of the report you have run | You can save your report in your chosen folder and return to it later | ALL countries
My Dashboard | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Hover over any coloured squares and ensure any absence records are showing correctly | Go to "Personal Dashboard" for the calendar | The detail of the absence records are correct and the tooltip contains the correct information | ALL countries
Check that the grey and white cells in the calendar accurately represent working pattern | Click them for more information | The grey cells represent a non-working day and the white cells represent a working day | ALL countries
Ensure personal information is correct | Scroll Down for the "Personal Information" section | Your personal information should be correct | ALL countries
Ensure entitlement pots are showing correct values | Look for "Entitlement Information" | You should only see entitlements that are relevant to you and these values should represent the data provided | ALL countries
Holidays & Planned Absences | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Book a planned absence for yourself | Click on the "book time off button" | The absence will be booked and a message will be displayed to confirm this - your manager should receive an email | ALL countries
Approve/Reject an absence record on behalf of someone else via email (only if you are an authoriser) | If a reportee places a request, you'll receive an email notification to approve it if you are their authoriser | Once your reportee has submitted an absence you should receive an email, there will be 2 buttons to approve/reject - clicking one of these should action the request | ALL countries
Approve/Reject an absence record on behalf of someone else via the manager dashboard (only if you are an authoriser) | As above, but go to "Manager Dashboard" under "Manager Tools" and find "Absences awaiting authorisation" | Once your reportee has submitted an absence, navigate to the Manager Dashboard and visit your "Action list to approve/reject - clicking one of these should action the request | ALL countries
Sickness & Unplanned Absences | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Book an unplanned absence for yourself (if available to book based on sickness absence type booking settings) | Go to "Unplanned Absences" under the "My Tools" section at the top of the screen and click "log sickness" | The absence will be booked and a messager will be displayed to confirm this - your manager should receive an email | ALL countries
Record Overtime & TOIL | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Record an instance of TOIL | Go to "Record overtime and TOIL" under the "My Tools" section at the top of the screen and click "log overtime and TOIL" | The absence will be booked and a message will be displayed to confirm this - your manager should receive an email | ALL countries
Calendar | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Hover over existing absences to confirm the right level of detail is displayed | Go to "Personal Dashboard" for the calendar | The expected behavior of this test will depend on the visibility settings provided on the Absence Types tab in your data capture form | ALL countries
Admin Link | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Click the 'Admin' button and ensure you are taken to the Admin Panel homepage | Click "Admin Panel" under "Admin Tools" at th top of the screen | If you have the role of an administrator you should be taken to the Admin panel | ALL countries
Online Help | How/Where | Expected Behaviour | User Testing This Feature | Additional Users Involved
Click online help button on any screen in e-days, check you are directed to https://support.e-days.com/support/home | Towards the top of the screen | You will be directed to the Edays support portal | ALL countries

## Config (hidden)
Status List
Completed - Expected Behaviour
Completed - Unexpected Behaviour